MIGRATION PROGRAMME

Technical Requirements Document

Server, Database & File Share Migration to AWS

| Customer | Enterprise Financial Services Organisation (AWS Customer) |
| --- | --- |
| Document Type | Technical Requirements Document (TRD) |
| Migration Scope | Servers (MGN) ¦ Databases (DMS) ¦ File Shares (DataSync) |
| Target Environment | AWS — ap-south-1 (Mumbai) ¦ DR: ap-southeast-1 (Singapore) |
| Document Version | v1.0 ¦ Issued for AWS ProServe Partner Review |

# 1. Introduction & Programme Context

## 1.1 Background

The organisation operates a large on-premise data centre hosting 300+ physical and virtual servers, 80+ databases, and 200+ TB of file share data across NFS and SMB/CIFS storage. The infrastructure supports core banking operations, risk analytics, customer data platforms, and back-office processing systems.

The organisation has approved a three-year cloud transformation programme to migrate the entire data centre footprint to AWS. This document defines the technical requirements for Phase 1 of the migration programme, which covers the tooling setup and pilot migration of a representative set of workloads using AWS Application Migration Service (MGN), AWS Database Migration Service (DMS), and AWS DataSync.

## 1.2 Programme Objectives

- Migrate 300+ on-premise servers to AWS EC2 with minimal downtime using AWS MGN block-level replication.

- Migrate 80+ databases (Oracle, SQL Server, MySQL, PostgreSQL) to AWS RDS and Aurora using AWS DMS with zero data loss.

- Migrate 200+ TB of NFS and SMB file share data to Amazon EFS, FSx for Windows, and S3 using AWS DataSync.

- Complete Phase 1 (tooling setup + pilot migration of 10 servers, 5 databases, and 2 file shares) within 3 months.

- Establish reusable migration patterns, runbooks, and automation scripts applicable to all subsequent migration waves.

- Achieve zero data loss for all database migrations and cryptographic checksum validation for all file share transfers.

## 1.3 Migration Approach

The programme adopts a lift-and-shift (rehost) approach for servers using MGN, a heterogeneous and homogeneous database migration approach using DMS, and an online transfer approach for file shares using DataSync. All three tools will operate in parallel during each migration wave.

| Migration Stream | AWS Service | Migration Strategy | Pilot Scope |
| --- | --- | --- | --- |
| Server Migration | AWS MGN | Rehost (lift-and-shift) via block-level replication | 10 servers: 5 Linux, 5 Windows |
| Database Migration | AWS DMS | Homogeneous + Heterogeneous (Oracle→Aurora, SQL Server→RDS SQL Server, MySQL→Aurora MySQL) | 5 databases: 1 Oracle, 2 SQL Server, 2 MySQL |
| File Share Migration | AWS DataSync | Online transfer with integrity validation | 2 shares: 1 NFS (5 TB), 1 SMB (3 TB) |

# 2. Source Environment Inventory

## 2.1 On-Premise Infrastructure Overview

| Category | Detail |
| --- | --- |
| Hosting Environment | Private data centre — co-located facility, Mumbai. Dual power feeds, N+1 cooling. |
| Hypervisor | VMware vSphere 7.0 (primary), Physical bare-metal servers (10% of estate) |
| Server OS Distribution | RHEL 7/8: 120 servers, CentOS 7: 60 servers, Windows Server 2016/2019: 120 servers |
| Total Server Count | 300 servers (250 VMs, 50 physical) |
| Database Engines | Oracle 12c/19c: 30 DBs, SQL Server 2016/2019: 25 DBs, MySQL 5.7/8.0: 15 DBs, PostgreSQL 11/13: 10 DBs |
| Total DB Count | 80 databases — combined size ~18 TB |
| File Share Infrastructure | NetApp ONTAP (NFS) — 120 TB, Windows File Server (SMB) — 80 TB, Total: 200+ TB |
| Network to AWS | AWS Direct Connect — 1 Gbps dedicated circuit (Mumbai). VPN backup: 500 Mbps site-to-site. |
| Migration Hub | AWS Migration Hub configured in ap-south-1 for centralised tracking. |

## 2.2 Pilot Workload Detail — Server Migration (MGN)

| Server Name | OS | vCPU | RAM (GB) | Storage (GB) | Application | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| web-app-01 | RHEL 8 | 4 | 16 | 100 | Customer portal web tier | P1 |
| web-app-02 | RHEL 8 | 4 | 16 | 100 | Customer portal web tier | P1 |
| app-svc-01 | RHEL 7 | 8 | 32 | 200 | Core banking app service | P1 |
| app-svc-02 | CentOS 7 | 8 | 32 | 200 | Risk analytics service | P2 |
| batch-01 | CentOS 7 | 4 | 16 | 150 | Nightly batch processing | P2 |
| win-app-01 | Win 2019 | 4 | 16 | 200 | Internal HR application | P2 |
| win-app-02 | Win 2019 | 4 | 16 | 200 | Document management | P2 |
| win-app-03 | Win 2016 | 8 | 32 | 300 | Financial reporting | P1 |
| db-proxy-01 | RHEL 8 | 4 | 16 | 100 | Database connection proxy | P1 |
| mon-svc-01 | RHEL 8 | 4 | 8 | 100 | Monitoring / Prometheus | P3 |

## 2.3 Pilot Workload Detail — Database Migration (DMS)

| DB Name | Engine | Version | Size | Source Host | Target Engine | Migration Type |
| --- | --- | --- | --- | --- | --- | --- |
| COREBANKING_DB | Oracle | 19c | 4 TB | oracle-prod-01 | Amazon Aurora PostgreSQL | Heterogeneous |
| RISKANALYTICS_DB | SQL Server | 2019 | 1.5 TB | sqlsrv-prod-01 | RDS SQL Server 2019 | Homogeneous |
| REPORTING_DB | SQL Server | 2016 | 800 GB | sqlsrv-prod-02 | RDS SQL Server 2019 | Homogeneous |
| CUSTOMER_DB | MySQL | 8.0 | 600 GB | mysql-prod-01 | Aurora MySQL 3.x | Homogeneous |
| PRODUCT_DB | MySQL | 5.7 | 400 GB | mysql-prod-02 | Aurora MySQL 3.x | Homogeneous |

## 2.4 Pilot Workload Detail — File Share Migration (DataSync)

| Share Name | Protocol | Storage System | Size | File Count | Target AWS Service | Priority |
| --- | --- | --- | --- | --- | --- | --- |
| /data/finreports | NFS v3 | NetApp ONTAP | 5 TB | 2.1 M files | Amazon EFS (General Purpose) | P1 |
| \\filsrv\customerdata | SMB/CIFS | Windows File Server 2019 | 3 TB | 1.4 M files | Amazon FSx for Windows File Server | P1 |

# 3. Technical Requirements — AWS MGN (Server Migration)

## 3.1 Functional Requirements

| Req ID | Requirement | Priority | Acceptance Criterion |
| --- | --- | --- | --- |
| MGN-FR-01 | AWS MGN must be initialised in ap-south-1 before any agent installation. Service-linked IAM roles must be created automatically by the service initialisation. | MUST | MGN console accessible in ap-south-1 with AWSServiceRoleForApplicationMigrationService created. |
| MGN-FR-02 | AWS Replication Agent must be installed on all 10 pilot source servers without requiring a server reboot. | MUST | Agent installation completes without reboot. Servers visible in MGN console with status 'Not Ready'. |
| MGN-FR-03 | Initial replication sync must complete within 48 hours for all pilot servers. Sync status must be 'Ready for testing' before test launch. | MUST | All 10 servers show sync lag < 1 second and status 'Ready for testing' within 48 hours. |
| MGN-FR-04 | Launch Template must be configured for each server: target instance type, subnet, security groups, IAM instance profile, and EBS volume configuration. | MUST | Launch Template configured and saved for each server before test launch. |
| MGN-FR-05 | Test instance launch and acceptance testing must be completed for all pilot servers before any cutover is initiated. | MUST | Test instances launched, application smoke tests passed, test instances terminated. |
| MGN-FR-06 | Cutover replication lag must be confirmed as 0 seconds before initiating cutover for each server. | MUST | MGN console shows 0-second lag. Verified by team lead before cutover command issued. |
| MGN-FR-07 | Post-launch actions must be configured to: join Windows servers to domain, update application configuration files with new IP/endpoint addresses, and start application services. | MUST | Post-launch actions execute successfully on all test and cutover instances. |
| MGN-FR-08 | Source servers must be archived in MGN within 48 hours of successful cutover confirmation. | SHOULD | Archived servers appear in MGN console under 'Archived Servers'. |

## 3.2 Non-Functional Requirements — MGN

| Req ID | Requirement | Target |
| --- | --- | --- |
| MGN-NFR-01 | Replication data must be encrypted in transit using TLS 1.2 or higher. | All replication traffic over port 1500 (TCP) encrypted with TLS. |
| MGN-NFR-02 | Cutover window must not exceed 1 hour per server (from source stop to target application healthy). | ≤ 60 minutes per server cutover. |
| MGN-NFR-03 | Replication server (staging area) must not be accessible from the public internet. | Replication servers in private subnet only. No public IP. |
| MGN-NFR-04 | Target EC2 instances must use the same EBS volume type as source or better (gp3 minimum). | All migrated instances use gp3 EBS volumes. |
| MGN-NFR-05 | MGN must support the agentless vCenter option for VMware VMs where OS-level agent installation is restricted. | Agentless replication configured for restricted VMs. |

# 4. Technical Requirements — AWS DMS (Database Migration)

## 4.1 Functional Requirements

| Req ID | Requirement | Priority | Acceptance Criterion |
| --- | --- | --- | --- |
| DMS-FR-01 | DMS Replication Instance must be deployed in a Multi-AZ configuration in the migration VPC private subnet. Instance class: dms.r5.xlarge minimum for pilot. | MUST | Replication instance deployed, status 'Available', Multi-AZ = true. |
| DMS-FR-02 | Source endpoints must be created for all 5 pilot databases with SSL mode 'verify-full'. Connection test must pass before task creation. | MUST | All source endpoints show 'Successful' connection test in DMS console. |
| DMS-FR-03 | Target endpoints must be created for all 5 AWS target databases (Aurora PostgreSQL, RDS SQL Server, Aurora MySQL). Connection test must pass. | MUST | All target endpoints show 'Successful' connection test. |
| DMS-FR-04 | For the Oracle→Aurora PostgreSQL heterogeneous migration (COREBANKING_DB), AWS Schema Conversion Tool (SCT) must be used to convert the schema before DMS task creation. All SCT action items of severity 'Error' must be resolved. | MUST | SCT migration assessment report shows 0 Error-level action items before DMS task start. |
| DMS-FR-05 | All DMS migration tasks must be configured as 'Full Load + CDC' to enable ongoing replication after initial full load, supporting zero-downtime cutover. | MUST | All 5 tasks configured with migration type = full-load-and-cdc. |
| DMS-FR-06 | Oracle source databases must have Supplemental Logging enabled at the database level before DMS CDC tasks are started. | MUST | Oracle supplemental logging confirmed: SELECT SUPPLEMENTAL_LOG_DATA_MIN FROM V$DATABASE = YES. |
| DMS-FR-07 | SQL Server source databases must have MS-CDC (Change Data Capture) enabled on all tables to be migrated. | MUST | sys.databases shows is_cdc_enabled = 1 for RISKANALYTICS_DB and REPORTING_DB. |
| DMS-FR-08 | Data validation must be enabled on all DMS tasks. Validation summary report must show 0 mismatched rows before cutover approval. | MUST | DMS validation report: Validation-succeeded rows = Total rows. Zero mismatches. |
| DMS-FR-09 | Table mapping rules must exclude system tables, temporary tables, and replication metadata tables from migration scope. | MUST | Table mapping JSON includes explicit exclude-schema rules for system schemas. |
| DMS-FR-10 | DMS task logs must be published to CloudWatch Logs. Log retention must be set to 90 days. | MUST | CloudWatch log group /aws/dms/tasks/{task-id} exists with 90-day retention. |

## 4.2 Non-Functional Requirements — DMS

| Req ID | Requirement | Target |
| --- | --- | --- |
| DMS-NFR-01 | Full load phase must complete within the agreed migration window. COREBANKING_DB (4 TB) must complete full load within 12 hours. | Full load ≤ 12 hours for 4 TB Oracle source. |
| DMS-NFR-02 | CDC replication lag must be maintained below 30 seconds during steady-state ongoing replication. | CDC lag ≤ 30 seconds measured over 24-hour period. |
| DMS-NFR-03 | Replication instance storage must not exceed 85% utilisation during migration. Auto-scaling must be configured. | DMS storage CloudWatch alarm at 85% threshold. |
| DMS-NFR-04 | All data in transit between source database and DMS replication instance must be encrypted using SSL. | SSL mode = verify-full on all source and target endpoints. |
| DMS-NFR-05 | DMS must support LOB (Large Object) column migration for Oracle BLOB/CLOB columns in COREBANKING_DB. | LOB settings: Limited LOB mode, max LOB size = 64 KB unless full LOB required. |

# 5. Technical Requirements — AWS DataSync (File Share Migration)

## 5.1 Functional Requirements

| Req ID | Requirement | Priority | Acceptance Criterion |
| --- | --- | --- | --- |
| DS-FR-01 | DataSync agent must be deployed as a VMware OVA in the on-premise environment. Agent must be activated and registered in the ap-south-1 AWS region before any transfer task is created. | MUST | Agent appears in DataSync console with status 'Online'. |
| DS-FR-02 | Source locations must be created for both pilot file shares: NFS location for /data/finreports and SMB location for \\filsrv\customerdata. | MUST | Both source locations created and verified in DataSync console. |
| DS-FR-03 | Target locations must be created: Amazon EFS file system for NFS share and Amazon FSx for Windows for SMB share. | MUST | Target EFS and FSx created, DataSync locations verified. |
| DS-FR-04 | DataSync transfer tasks must be configured with data integrity verification enabled (BEST_EFFORT or ONLY_FILES_TRANSFERRED based on share size). | MUST | Verify data = BEST_EFFORT for NFS (5 TB), ONLY_FILES_TRANSFERRED for SMB (3 TB). |
| DS-FR-05 | File metadata must be preserved during transfer: timestamps (mtime, atime), POSIX permissions for NFS, NTFS permissions (ACLs) for SMB. | MUST | Post-transfer spot-check: file permissions and timestamps match source for 100-file random sample. |
| DS-FR-06 | Transfer tasks must support incremental (delta) transfers — subsequent task executions must only transfer new or modified files. | MUST | Second task execution transfers only changed files. Task execution report shows Files Transferred < Total Files. |
| DS-FR-07 | DataSync must use a VPC endpoint to transfer data over the Direct Connect circuit without traversing the public internet. | MUST | DataSync traffic visible on Direct Connect CloudWatch metrics. No traffic on public IP. |
| DS-FR-08 | Transfer schedule must support recurring execution (daily incremental sync) in the run-up to cutover to minimise delta at cutover time. | MUST | Task schedule configured: daily at 02:00 IST. Schedule visible in DataSync console. |
| DS-FR-09 | DataSync task execution logs must be published to CloudWatch Logs. Notification must be sent via SNS on task failure. | MUST | CloudWatch log group for DataSync tasks. SNS alert on FAILED execution status. |

## 5.2 Non-Functional Requirements — DataSync

| Req ID | Requirement | Target |
| --- | --- | --- |
| DS-NFR-01 | Transfer throughput must utilise at least 70% of available Direct Connect bandwidth during scheduled transfer windows. | ≥ 700 Mbps sustained throughput during transfer window. |
| DS-NFR-02 | Initial full transfer of 5 TB NFS share must complete within 18 hours. SMB 3 TB share within 12 hours. | NFS: ≤ 18 hours. SMB: ≤ 12 hours. |
| DS-NFR-03 | DataSync agent must be deployed with redundancy — two agent VMs deployed for failover. Tasks configured with both agents. | 2 agent VMs deployed. Task lists both agents. |
| DS-NFR-04 | All data in transit must be encrypted using TLS 1.2 or higher. | DataSync uses TLS by default. VPC endpoint ensures private transit. |
| DS-NFR-05 | Final cutover sync (last delta before file share cutover) must complete within 2 hours. | Final delta sync ≤ 2 hours for both shares combined. |

# 6. Networking & Security Requirements

## 6.1 Network Architecture

On-Premise Data Centre (Mumbai Co-Lo)

└─ AWS Direct Connect (1 Gbps) → DX Gateway → Transit Gateway (ap-south-1)

└─ Migration VPC (10.100.0.0/16)

├─ Public Subnet (10.100.1.0/24) — NAT Gateway only

├─ Private Subnet AZ-a (10.100.10.0/24) — MGN Replication Servers, DMS Replication Instance

├─ Private Subnet AZ-b (10.100.11.0/24) — MGN Replication Servers (HA)

└─ DataSync VPC Endpoint — Interface endpoint in private subnets

Target Application VPC (10.200.0.0/16)

├─ Public Subnets (ALB, NAT GW)

├─ Private App Subnets (EC2 — migrated servers)

├─ Private DB Subnets (RDS, Aurora — migrated databases)

└─ EFS Mount Targets, FSx interfaces (migrated file shares)

## 6.2 Firewall & Security Group Requirements

| Req ID | Requirement | Port / Protocol | Source → Destination |
| --- | --- | --- | --- |
| NET-01 | MGN replication agent communication | TCP 443 (HTTPS) | Source servers → MGN service endpoint (via DX) |
| NET-02 | MGN block replication data channel | TCP 1500 | Source servers → MGN Replication Servers (staging) |
| NET-03 | DMS to Oracle source database | TCP 1521 | DMS Replication Instance → Oracle source host |
| NET-04 | DMS to SQL Server source | TCP 1433 | DMS Replication Instance → SQL Server source host |
| NET-05 | DMS to MySQL source | TCP 3306 | DMS Replication Instance → MySQL source host |
| NET-06 | DMS to target Aurora/RDS | TCP 5432 / 1433 / 3306 | DMS Replication Instance → Target DB endpoint |
| NET-07 | DataSync agent to AWS | TCP 443 (HTTPS) | DataSync Agent VM → DataSync VPC Endpoint |
| NET-08 | DataSync agent to NFS share | TCP/UDP 2049 | DataSync Agent VM → NetApp ONTAP NFS server |
| NET-09 | DataSync agent to SMB share | TCP 445 | DataSync Agent VM → Windows File Server |

## 6.3 IAM Requirements

- A dedicated IAM role (MigrationAdminRole) with the minimum permissions required to operate MGN, DMS, and DataSync must be created and used for all migration activities. No use of AdministratorAccess or PowerUserAccess.

- DMS replication instance must use a dedicated IAM role (dms-vpc-role) with AmazonDMSVPCManagementRole policy for VPC endpoint management.

- DataSync agent activation must use IAM credentials with datasync:CreateAgent permission only — not full DataSync admin rights.

- All migrated EC2 instances must have an IAM instance profile attached with SSM managed instance core permissions for post-migration management.

- KMS CMKs must be used to encrypt: EBS volumes of migrated EC2 instances, RDS / Aurora target databases, EFS and FSx file systems.

# 7. Pilot Migration Phases & Timeline

## 7.1 Phase Plan

| Phase | Duration | Key Activities | Exit Criteria |
| --- | --- | --- | --- |
| 0 — Setup | Week 1–2 | IAM roles, networking, VPC endpoints, Landing Zone validation, CMF integration, Migration Hub setup. | All prerequisites verified. Go/No-Go from security team. |
| 1 — Tool Initialisation | Week 2–3 | MGN initialised (console + replication settings). DMS replication instance deployed. DataSync agents deployed and activated. | All tools show healthy status. Connection tests passing. |
| 2 — Replication Setup | Week 3–5 | MGN agents installed on 10 servers. Initial sync completed. DMS endpoints created, SCT executed for Oracle migration. DataSync tasks created. Initial transfer started. | All 10 servers 'Ready for testing'. DMS tasks running. DataSync initial transfer complete. |
| 3 — Test Launch | Week 5–6 | MGN test instances launched. Application testing on all 10 servers. DMS data validation. DataSync data integrity check. | Test pass sign-off from application owners. DMS 0 mismatches. DataSync checksum verified. |
| 4 — Cutover | Week 7 | Final delta sync. Source stop. MGN cutover. DMS CDC stop + final sync. DataSync final delta. DNS cutover. | All 10 servers running on AWS. Databases accessible on RDS/Aurora. File shares accessible on EFS/FSx. |
| 5 — Hypercare | Week 7–9 | 2-week monitored production operation. Issue triage. Runbook updates. Wave 1 planning begins. | No P1 incidents for 5 consecutive business days. Hypercare sign-off by customer. |

# 8. Monitoring & Observability Requirements

- CloudWatch dashboard covering: MGN replication lag per server, DMS task latency and error rates, DataSync task throughput and file counts, EC2 instance health post-migration, RDS instance metrics (CPU, connections, storage).

- SNS alerts must be configured for: MGN replication lag > 60 seconds, DMS task error or stopped state, DataSync task execution failure, post-migration EC2 instance unhealthy status check.

- Migration Hub must reflect real-time status of all 10 server migrations, 5 database migrations, and 2 file share migrations.

- DMS task CloudWatch metrics to monitor: CDCLatencySource, CDCLatencyTarget, FullLoadThroughputRowsSource, ValidationPendingRecords.

- All migration-related API calls must be logged in CloudTrail. CloudTrail logs must be forwarded to a centralised S3 bucket with a 1-year retention policy.

# 9. Acceptance Criteria Summary

| AC ID | Stream | Acceptance Criterion | Verifier |
| --- | --- | --- | --- |
| AC-01 | MGN | All 10 pilot servers migrated to AWS EC2 and running without P1 application errors for 48 hours post-cutover. | Application owners |
| AC-02 | MGN | Cutover window for each server ≤ 60 minutes from source stop to target application healthy. | Migration lead |
| AC-03 | DMS | Zero data loss confirmed by DMS validation report (0 mismatched rows) for all 5 databases. | DBA team |
| AC-04 | DMS | CDC replication lag sustained < 30 seconds for 24 hours before cutover date. | DBA team |
| AC-05 | DataSync | File count and total bytes on target match source for both file shares (validated by DataSync task report). | Storage team |
| AC-06 | DataSync | File metadata (permissions, timestamps) preserved — spot-check 100 random files per share. | Storage team |
| AC-07 | All | Zero critical security findings on migrated infrastructure after AWS Security Hub scan. | Security team |
| AC-08 | All | All migration activities logged in Migration Hub. Final wave report generated. | Migration lead |

CONFIDENTIAL — AWS Customer — Migration Programme TRD v1.0